## Slide 1
Inside Sherpa – Digital Internship
Technology, Strategy & Architecture – Technology Optimisation & Delivery Module
7 JULY2020

## Slide 2: Project Plan for SectorMetric This project plan will outline how Deloitte will deliver this technology evaluation and selection engagement.
Our scope will include the following:
Providing a framework for exception led requirement gathering and use case development.
Initial market long list of proposed technology solutions.
Market scan approach and scoring methodology.
Technology evaluation matrix template and guidance.
Our initial understanding of risks, issues and dependencies are as follows:
You acknowledge that our ability to deliver this piece of work is dependent on you meeting your responsibilities. If responsibilities are not conducted in a timely manner, these will affect project budget, timelines and scope.
Resource constraints (both internal and client) is a risk that may impact delivery timelines.
Lack of availability of Subject Matter Experts and relevant
stakeholders may present a risk to delivery timelines.
Availability and agreement of vendors to respond within the
timeframes assumed (within a week’s notice) for demos, pricing and
contracts discussions.
Our understanding of the scope Risks, issues and dependencies

## Slide 3: Project Plan for SectorMetric This project plan will outline how Deloitte will deliver this technology evaluation and selection engagement.
Our proposed resource plan and estimation of fees is as below:
Initial project timeline Resource plan and estimation of fees
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Phase
Phase 1
Phase 2
Stakeholder Meeting
Milestone Stakeholder meeting
Our proposed engagement timelines will span for the total of 6 weeks. In this timeframe we proposed the following phases:
Phase 1 Technology Evaluation – Consists of providing a framework for exception led requirement gathering and use case development.
Phase 2 Technology Analysis and Selection – Consist of developing market scan approach and scoring methodology.
Our proposed project timeline is as follows:
Position | Daily rate not incl. GST | Number of days over 6 weeks | Total
Partner | $3500 | 2 | $7,000
Director | $3000 | 6 | $18,000
Senior Consultant | $1200 | 30 | $36,000
Senior Consultant | $1200 | 30 | $36,000
 |  | Total | $97,000

## Slide 4
Deloitte refers to one or more of Deloitte Touche Tohmatsu Limited (“DTTL”), its global network of member firms, and their related entities. DTTL (also referred to as “Deloitte Global”) and each of its member firms are legally separate and independent entities. DTTL does not provide services to clients. Please see www.deloitte.com/about to learn more.
About Deloitte
Deloitte is a leading global provider of audit and assurance, consulting, financial advisory, risk advisory, tax and related services. Our network of member firms is in more than 150 countries and territories. Learn how Deloitte’s approximately 264,000 people make an impact that matters at www.deloitte.com.
About Deloitte Australia
In Australia, the member firm is the Australian partnership of Deloitte Touche Tohmatsu and is one of Australia’s leading professional services firms. Focused on the creation of value and growth, and known as an employer of choice for innovative human resources programs, we are dedicated to helping our clients and our people excel. For more information, please visit our web site at www.deloitte.com.au.
Liability limited by a scheme approved under Professional Standards Legislation. Member of Deloitte Touche Tohmatsu Limited
© 2019 Deloitte Consulting Pty Ltd.
PUBLIC